## product backlog
User Story | Description | Assigned To | Status | Comments
1 | Design and functionality feed page (Android) | Celeste | Working
2 | Design and functionality history page (Android) | Celeste | Working
3 | Design and functionality database schema (Android) | Celeste | Working
4 | Design and functionality homepage (Android) | Celeste | Working
5 | Design and functionality login page (Android) | Celeste | Working
6 | Design and functionality registration page (Android) | Celeste | Working
7 | Design and functionality post issue page (Android) | Prateek | Working
8 | Design and functionality preview submit page (Android) | Celeste | Working
9 | Design and functionality settings page (Android) | Celeste | Working
10 | Create database | Rafif | Done
11 | Create AWS instance and setup web server | Akshay | Done
12 | Setup python flask app for CMS and API | Maha | Working
13 | Create Api doc | Akshay | Working
14 | Create Api for login and registration | Pranay, Sonali | Working
15 | Create Api for post issue and get issue feed/history | Pranay, Sonali
16 | Create Api for forgot and reset password | Pranay, Sonali
17 | Create Api for update settings | Pranay, Sonali
18 | Create Api for add maintenance personnel | Pranay, Sonali |  | This api is merged with registration api.
19 | Create Api to get list of users | Pranay, Sonali
20 | Create Api to information about particular issue, user | Pranay, Sonali
21 | Create Api to update issue, user or maintenance person | Pranay, Sonali |  | This api is merged with update issue api
22 | Create Api to assign issue to a maintenance person | Pranay, Sonali |  | This api can be included in update issue api.
23 | Create api to add category, priorities from CMS | Pranay, Sonali
24 | Create api to update categories, priorities from CMS | Pranay, Sonali
25 | Create api to delete categories, priorities from CMS | Pranay, Sonali
26 | Create login, home page in CMS | Maha, Rafif | Working | There will be filter option on pages where lists are showing like on issue list page, issue must be filtered on basis of assigned maintenance person or issue category or time or location or priority.
27 | Create page to list reported issue | Maha, Rafif
28 | Create add maintenance personnel page, maintenance person profile page | Maha, Rafif
29 | Create issue page to see any particular issue, user profile page to see any particular user information | Maha, Rafif |  | There will be option of assigning issue to maintenance person on issue page.
30 | Create user list page, maintenance personnel list page | Maha, Rafif
31 | Create page to add, update or delete categories and priorities in CMS | Maha, Rafif
32 | Fill database tables categories and priorities | Rafif

## Oct23 - Oct27
User Story | Description | Assigned To | Status | Comments
1 | Design and functionality feed page (Android) | Celeste | Working | Making design changes to make the application more user friendly and appealing
2 | Design and functionality history page (Android) | Celeste | Working
3 | Design and functionality database schema (Android) | Celeste | Working
4 | Design and functionality homepage (Android) | Celeste | Working
5 | Design and functionality login page (Android) | Celeste | Working
6 | Design and functionality registration page (Android) | Celeste | Working
7 | Design and functionality post issue page (Android) | Prateek | Working
8 | Design and functionality preview submit page (Android) | Celeste | Working
9 | Design and functionality settings page (Android) | Celeste | Working
10 | Create database | Rafif | Done
11 | Create AWS instance and setup web server | Akshay | Done
12 | Setup python flask app for CMS and API | Maha | Working
13 | Create Api doc | Akshay | Working
14 | Create Api for login and registration | Pranay, Sonali | Working
15 | Create login, home page in CMS | Maha, Rafif | Working