## product backlog
User Story | Description | Assigned To | Status
1 | Design feed page | Maha | Done
2 | Design history page | Maha | Done
3 | Design database schema | Maha | Done
4 | Design homepage | Sonali | Done
5 | Design login page | Sonali, Pranay | Done
6 | Design registration page | Rafif | Done
7 | Design post issue page | Akshay | Done
8 | Design preview submit page | Akshay | Done
9 | Design settings page | Akshay, Rafif | Done
10 | add functionality feed page | Maha | Done
11 | add functionality to history page | Maha | Done
12 | Add functionality to registration page | Rafif | Done
13 | Add additional validations to registration page | Rafif | Done
14 | Create database | Rafif | Done
15 | Create database table - Users | Rafif | Done
16 | Create database table - Maintenance | Rafif | Done
17 | Create database table - Issues | Rafif | Done
18 | Create database table - Category | Rafif | Done
19 | Create database table - Issues_category | Rafif | Done
20 | Fill database tables | Rafif | Done
21 | Create AWS instance | Maha | Done
22 | Design web portal | Maha | working
23 | Deploy flask on AWS | Maha | Done
24 | log in functionality | Celeste | working
25 | forgot password | Celeste | working
26 | location permission | Celeste | working
27 | settings page | Celeste | working
28 | camera access | Celeste | working
29 | gallery access | Celeste | working
30 | issue description | Celeste | working
31 | page navigation | Celeste | working
32 | Develop Login API | Pranay | Done
33 | Develop Registration API | Pranay | Done
34 | Testing Login, Registration API calls with SQLITE db on localhost with Postman | Pranay | In progress
35 | Integration of Login, Registration API calls with respective Android screens | Pranay, Sonali | In progress
36 | Testing Login and Registration end-to-end flows with EC2 instance | Pranay, Sonali | In progress
37 | API for All issues(Feed) | Sonali | In progress
Note on C10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Oct23 - Oct27
User Story | Description | Assigned To | Status | Comments
1 | Create AWS instance | Maha | Done
2 | Design web portal | Maha | Working
3 | Deploy flask on AWS | Maha | Done
4 | Add additional validations to registration page | Rafif | Done
5 | Create database | Rafif | Done
6 | Create database table - Users | Rafif | Done
7 | Create database table - Maintenance | Rafif | Done
8 | Create database table - Issues | Rafif | Done
9 | Create database table - Category | Rafif | Done
10 | Create database table - Issues_category | Rafif | Done
11 | Fill database tables | Rafif | Done
12 | Design changes in mobile app | Celeste | Working | Making design changes to make the application more user friendly and appealing
13 | Login API Connection from Android side | Celeste | Working | Will start working when API is set up on the server side
14 | Registration API Connection from Android side | Celeste | Working | Will start working when API is set up on the server side
15 | Develop Login API | Pranay | Done
16 | Develop Registration API | Pranay | Done
17 | Testing Login, Registration API calls with SQLITE db on localhost with Postman | Pranay | In progress
18 | Integration of Login, Registration API calls with respective Android screens | Pranay, Sonali | In progress
19 | Testing Login and Registration end-to-end flows with EC2 instance | Pranay, Sonali | In progress
20 | API for All issues(Feed) | Sonali | In progress
prof want to do items
rafir and prateek what?