## product backlog
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Design feed page |  | Maha | Done | sprint 1
2 | Design history page |  | Maha | Done | sprint 1
3 | Design database |  | Maha | Done | sprint 1
4 | Design homepage |  | Sonali | Done | sprint 1
5 | Design login |  | Sonali | Done | sprint 1
6 | Design registration page |  | Rafif | Done | sprint 1
7 | Design post issue page |  | Akshay | Done | sprint 1
8 | Design preview submit page |  | Akshay | Done | sprint 1
9 | Design settings page |  | Akshay | Done | sprint 1
10 | add functionality feed page |  | Maha | Done | sprint 2
11 | add functionality to history page |  | Maha | Done | sprint 2
12 | log in functionality |  | Sonali | working | sprint 2
13 | forgot password |  | Sonali | working | sprint 2
14 | location permission |  | Sonali | working | sprint 2
15 | settings page |  | Akshay | working | sprint 2
16 | camera access |  | Akshay | working | sprint 2
17 | gallery access |  | Akshay | working | sprint 2
18 | issue description |  | Sonali | working | sprint 2
19 | page navigation |  | Sonali | working | sprint 2
20
21
22
23
24
25
26
27
28
29
30
31
32
33
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 1
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Design feed page |  | Maha | Done
2 | Design history page |  | Maha | Done
3 | Design database |  | Maha | Done
4 | Design homepage
5 | Design login
6 | Design registration page
7 | Design post issue page
8 | Design preview submit page
9
10
11
12
13
14
15
16
17
18
19
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 2
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | add functionality feed page |  | Maha | working
2 | add functionality to history page |  | Maha | working
3 | log in functionality
4 | forgot password
5 | location permission
6 | settings page
7 | camera access
8 | gallery access
9 | issue description
10 | page navigation
11
12
13
| Handle web scraping exceptions - connection |  | Rafif | Done
| fetch categories |  | Maha | Done
| fetch full description |  | Maha, Akshay,Rafif | Done
| Handle db exceptions - connection |  | Maha,pranay | Done
| Handle db exceptions - data type |  | Maha,Rafif | Done
| Handle db exceptions - empty list |  | Maha | Done
| Handle db exceptions - add only new events |  | Maha | Done
| Fill db - category table |  | Maha | Done
| Fill db - event category table |  | Rafif | Done
| Fill db - event table |  | Maha | Done
| Fill - last updated table |  | Maha, Rafif | Done
| Setup web server |  | Akshay | Done
| Finish design part and start work on api (ios) |  | Akshay | Done

## Sprint 3
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Create db |  | Maha | Done | Login, Registration and forgot password done.
2 | Handle db exceptions |  | Maha | Working
3 |  |  | Maha | Done | Login, Registration and forgot password done.
4 | Create log file for api request and response |  | Pranay, Prateek | Working
5 | My feed Screen logic |  | Sonali
6 | My Subscription logic |  | Sonali

## Sprint 4
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Finish api integration in ios |  | Akshay | Working
3 | Create and finish api methods |  | Pranay, Sonali | Working | Login, Registration and forgot password done.
4 | Create log file for api request and response |  | Pranay, Prateek | working
5 | Start work on api in android |  | Sonali
6
7 | Cron job - add new events and delete past event |  | Maha, Rafif, Akshay | working