## product backlog
User Story | Description | Assigned To | Status | Comments
1 | Design feed page (Android) | Celeste | Done
2 | Design history page (Android) | Celeste | Done
3 | Design settings page (Android) | Celeste | Done
4 | Design homepage (Android) | Celeste | Done
5 | Design login page (Android) | Celeste | Done
6 | Design registration page (Android) | Celeste | Done
7 | Design post issue page (Android) | Celeste | Done
8 | Design preview submit page (Android) | Celeste | Done
9 | Design & functionality of about Page | Celeste | Done
10 | Functionality of post issuge page gallery | Celeste | Working
11 | Functionality feed page (Android) | Celeste | Working
12 | Functionality history page (Android) | Celeste | Working
13 | Functionality of post issue page | Celeste | Working
14 | Functionality homepage (Android) | Celeste | Working
15 | Functionality login page (Android) | Celeste | Working
16 | Functionality registration page (Android) | Celeste | Working
17 | Functionality post issue page Camera | Celeste | Done
18 | Functionality preview submit page (Android) | Celeste | Working
19 | Functionality settings page (Android) | Celeste | Working
20 | Create database | Rafif | Done
21 | Create AWS instance and setup web server | Akshay | Done
22 | Setup python flask app for CMS and API | Maha | Working
23 | Create Api doc | Akshay | Working
24 | Create Api for login and registration | Pranay, Sonali | Working
25 | Create Api for post issue and get issue feed/history | Pranay, Sonali
26 | Create Api for forgot and reset password | Pranay, Sonali
27 | Create Api for update settings | Pranay, Sonali
28 | Create Api for add maintenance personnel | Pranay, Sonali |  | This api is merged with registration api.
29 | Create Api to get list of users | Pranay, Sonali
30 | Create Api to information about particular issue, user | Pranay, Sonali
31 | Create Api to update issue, user or maintenance person | Pranay, Sonali |  | This api is merged with update issue api
32 | Create Api to assign issue to a maintenance person | Pranay, Sonali |  | This api can be included in update issue api.
33 | Create api to add category, priorities from CMS | Pranay, Sonali
34 | Create api to update categories, priorities from CMS | Pranay, Sonali
35 | Create api to delete categories, priorities from CMS | Pranay, Sonali
36 | Create Admin login | Maha | Done | login for admina and maintenance web portal
37 | Create Home Page ( admin protal) | Maha | Done | There will be filter option on pages where lists are showing like on issue list page, issue must be filtered on basis of assigned maintenance person or issue category or time or location or priority.
38 | Forgot Password | Maha/Rafif | Working
39 | View Users ( admin protal) | Maha | Done
40 | Add Users ( admin protal) | Maha/Rafif | Working
41 | Update Users ( admin protal) | Maha/Rafif | Working
42 | View Admins ( admin protal) | Maha | Done
43 | Add Admin ( admin protal) | Maha/Rafif | Working
44 | Update Admin ( admin protal) | Maha/Rafif | Working
45 | Profile ( admin protal) | Maha/Rafif
46 | View Issues ( admin protal) | Maha | Done
47 | Assign Issues ( admin protal) | Maha/Rafif
48 | View Maintenances ( admin protal) | Maha | Done
49 | Add Maintenance ( admin protal) | Maha/Rafif | Working
50 | Update Maintenance ( admin protal) | Maha/Rafif | Working
51 | View priorities ( admin protal) | Maha/Rafif | Working
52 | Add priorities ( admin protal) | Maha/Rafif | Working
53 | Update priorities ( admin protal) | Maha/Rafif | Working
54 | View Categories ( admin protal) | Maha | Done
55 | Add Categories ( admin protal) | Maha/Rafif | Working
56 | Update Categories ( admin protal) | Maha/Rafif | Working
57 | View Notifications | Maha/Rafif
58 | Delete Notification | Maha/Rafif
59 | Fill database tables categories and priorities | Rafif | Done

## Oct23 - Oct27
User Story | Description | Assigned To | Status | Comments
1 | Design and functionality feed page (Android) | Celeste | Working | Making design changes to make the application more user friendly and appealing
2 | Design and functionality history page (Android) | Celeste | Working
3 | Design and functionality database schema (Android) | Celeste | Working
4 | Design and functionality homepage (Android) | Celeste | Working
5 | Design and functionality login page (Android) | Celeste | Working
6 | Design and functionality registration page (Android) | Celeste | Working
7 | Design and functionality post issue page (Android) | Prateek | Working
8 | Design and functionality preview submit page (Android) | Celeste | Working
9 | Design and functionality settings page (Android) | Celeste | Working
10 | Create database | Rafif | Done
11 | Create AWS instance and setup web server | Akshay | Done
12 | Setup python flask app for CMS and API | Maha | Done
13 | Create Api doc | Akshay | Working
14 | Create Api for login and registration | Pranay, Sonali | Done
15 | Create login, home page in CMS | Maha | Done
16 | View Users ( admin protal) | Maha | Done
17 | View Admins ( admin protal) | Maha | Done
18 | View Issues ( admin protal) | Maha | Done
19 | View Maintenances ( admin protal) | Maha | Done
20 | View Categories ( admin protal) | Maha | Done

## Oct30 - Nov3
User Story | Description | Assigned To | Status | Comments
18 | Create Api for add maintenance personnel | Pranay, Sonali | Working | This api is merged with registration api.
21 | Create Api to update issue, user or maintenance person | Pranay, Sonali | Working | This api is merged with update issue api
23 | Create api to add category, priorities from CMS | Pranay, Sonali | Working
24 | Create api to update categories, priorities from CMS | Pranay, Sonali | Working
| Add admin (admin portal) | Maha/Rafif | Working
| Update Admin ( admin protal) | Maha/Rafif | Working
| Add Maintenance (admin protal) | Maha/Rafif | Working
| Update Maintenance ( admin protal) | Maha/Rafif | Working
| View priorities ( admin protal) | Maha/Rafif | Working
| Add priorities ( admin protal) | Maha/Rafif | Working
| Update priorities ( admin protal) | Maha/Rafif | Working
| Add Categories ( admin protal) | Maha/Rafif | Working
| Update Categories ( admin protal) | Maha/Rafif | Working
| Work on forgot password connection to server | Celeste
| Work on capturing image | Celeste
| Work on settings connection to server | Celeste
| work on settings page design | Celeste
| work on login connection to server | Celeste
| work on register connection to server | Celeste
| working on gallery function | Celeste