## product backlog
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Design feed page |  | Maha | Done | sprint 1
2 | Design history page |  | Maha | Done | sprint 1
3 | Design database schema |  | Maha | Done | sprint 1
4 | Design homepage |  | Sonali | Done | sprint 1
5 | Design login |  | Sonali | Done | sprint 1
6 | Design registration page |  | Rafif | Done | sprint 1
7 | Design post issue page |  | Akshay | Done | sprint 1
8 | Design preview submit page |  | Akshay | Done | sprint 1
9 | Design settings page |  | Akshay, Rafif | Done | sprint 1
10 | add functionality feed page |  | Maha | Done | sprint 2
11 | add functionality to history page |  | Maha | Done | sprint 2
12 | Add functionality to registration page |  | Rafif | Done | Sprint 2
13 | Add additional validations to registration page |  | Rafif | Done | Sprint 3
14 | Create database |  | Rafif | Done | Sprint 3
15 | Create database table - Users |  | Rafif | Done | Sprint 3
16 | Create database table - Maintenance |  | Rafif | Done | Sprint 3
17 | Create database table - Issues |  | Rafif | Done | Sprint 3
18 | Create database table - Category |  | Rafif | Done | Sprint 3
19 | Create database table - Issues_category |  | Rafif | Done | Sprint 3
20 | Fill database tables |  | Rafif | Done | Sprint 3
21 | Create AWS instance |  | Maha | Done | Sprint 3
22 | Design web portal |  | Maha | working | Sprint 3
23 | Deploy flask on AWS |  | Maha | Done | Sprint 3
24 | log in functionality |  | Celeste | working | Sprint 3
25 | forgot password |  | Celeste | working | Sprint 3
26 | location permission |  | Celeste | working | Sprint 3
27 | settings page |  | Celeste | working | Sprint 3
28 | camera access |  | Celeste | working | Sprint 3
29 | gallery access |  | Celeste | working | Sprint 3
30 | issue description |  | Celeste | working | Sprint 3
31 | page navigation |  | Celeste | working | Sprint 3
32
33
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 1
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Design feed page |  | Maha | Done
2 | Design history page |  | Maha | Done
3 | Design database |  | Maha | Done
4 | Design homepage
5 | Design login
6 | Design registration page |  | Rafif | Done
7 | Design post issue page
8 | Design preview submit page
9 | Design setting page |  | Akshay, Rafif | Done
10
11
12
13
14
15
16
17
18
19
Note on D10: +ptyagi1@stevens.edu +pbure@stevens.edu Database maha and rafif are creating. You need to start work on api for fetching data from database and create methods so that application can get data from server. _Assigned to Prateek Tyagi_ -Akshay Sunderwani

## Sprint 2
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | add functionality feed page |  | Maha | Done
2 | add functionality to history page |  | Maha | Done
3 | log in functionality
4 | forgot password
5 | location permission
6 | settings page
7 | camera access
8 | gallery access
9 | issue description
10 | page navigation
11 | Add functionality to registration page |  | Rafif | Done
12
13

## Sprint 3
User Story | Description | Submit Date | Assigned To | Status | Comments
1 | Create AWS instance |  | Maha | Done
2 | Design web portal |  | Maha | working
3 | Deploy flask on AWS |  | Maha | Done
4 | Add additional validations to registration page |  | Rafif | Done
5 | Create database |  | Rafif | Done
6 | Create database table - Users |  | Rafif | Done
7 | Create database table - Maintenance |  | Rafif | Done
8 | Create database table - Issues |  | Rafif | Done
9 | Create database table - Category |  | Rafif | Done
10 | Create database table - Issues_category |  | Rafif | Done
11 | Fill database tables |  | Rafif | Done
12 | Design changes in mobile app |  | Celeste | Working | Making design changes to make the application more user friendly and appealing
13 | Login API Connection from Android side |  | Celeste | Working | Will start working when API is set up on the server side
14 | Registration API Connection from Android side |  | Celeste | Working | Will start working when API is set up on the server side